# CS 501, Software Engineering

# Quiz 1

Tuesday, February 5, 2002

30 minutes

## Instructions

1)  Answer both questions.

2)	Write your answers in an examination book. WRITE YOUR NETID ON THE FRONT OF EACH BOOK.

3)  This is an open book examination.   You may use any book or notes, but no computers.

## Question 1

The Piccadilly television advertising project is likely to have some sort of database.

(a)  	At what stage in the waterfall process, would the decision be made to use a relational database?  Give the reasons for your answer.

(b) 	At what stage in the waterfall process, would the decision be made to use an Oracle database?  Give the reasons for your answer.

(c) 	At what stage in the waterfall process would the database schema be specified?  Give the reasons for your answer.

## Question 2

Here is an activity graph with time estimates for each activity.

(a)	For each event, calculate:

(i)	the earliest start date

(ii)	the latest start date

(b)	For each activity, calculate the slack.

(c)	What is the critical path?

Solution to Question 2

Event	Earliest	Latest

start	start

A	0	0

B	8	8

C	5	10

D	11	11

E	16	16

F	20	20

G	22	22

Activity	Slack

AB	0

AC	5

AD	7

BD	0

BG	9

CE	5

DE	0

EF	0

EG	3

FG	0

Critical path is ABDEFG